### Comprehensive Go-to-Market Plan for Unique Healthy Food Product

#### Phase 1: Product Validation & Protection (0-3 months)

- Finalize proprietary recipe/formula and lock in IP

  - File provisional patent (if novel process/ingredient combo)

  - Trademark brand name, logo, and any unique claims

  - Execute NDAs with all early partners

- Conduct blind taste tests & concept testing

  - Minimum 200 target consumers (health-conscious 25-45, higher income)

  - Achieve ≥85% purchase intent at $X price point

- Complete nutritional & shelf-life validation

  - Third-party lab testing (macro/micro nutrients, allergens, pathogens)

  - Accelerated shelf-life study (target 12-18 months ambient or refrigerated)

- Secure food-safety certifications early

  - SQF or BRC audit booked

  - Non-GMO, Organic, Kosher, Gluten-Free, Vegan certifications as applicable

#### Phase 2: Supply Chain & Manufacturing (2-9 months)

- Identify & audit 2-3 co-packers

  - Require commercial runs ≥5,000 units/batch

  - Lock in 12-month capacity reservations

- Finalize ingredient sourcing

  - LOIs with all critical suppliers (especially unique ingredients)

  - Build 3-6 month safety stock of hero ingredients

- Costing & margin target

  - Landed COGS ≤30% of target retail price

  - Minimum 50% gross margin at scale

- Packaging development

  - Sustainable, recyclable, resealable where possible

  - Final dielines + printer proofs

  - UPC/EAN generation

#### Phase 3: Brand & Positioning (3-8 months parallel)

- Core brand platform

  - Name, tagline, mission, values

  - Unique Selling Proposition (e.g., “first ever X that tastes like Y but with Z health benefits”)

- Visual identity & packaging design

  - Hire top-tier food branding agency

  - Front-panel claim hierarchy finalized (health, taste, convenience)

- Content assets

  - Hero product photography & video

  - Founder story video

  - Clinical or chef endorsement assets

#### Phase 4: Regulatory & Compliance (4-10 months)

- FDA compliance (US focus)

  - Nutrition Facts Panel + ingredient deck finalized

  - Structure/function claims reviewed by regulatory counsel

  - Submit for GRAS if novel ingredient

- Insurance

  - $5-10M product liability + recall insurance locked

#### Phase 5: Launch Strategy & Channel Plan

Priority 1 – Direct-to-Consumer (60-70% of Year 1 revenue)

- Shopify Plus store live 60 days pre-launch

- Klaviyo email/SMS flows built

- Meta + TikTok ad accounts pre-warmed

- Subscription model (20-30% discount for subscribe & save)

Priority 2 – Specialty Retail & E-commerce Partners

- Erewhon, Whole Foods, Sprouts buyer presentations (Month 6-8)

- Thrive Market, Amazon Fresh, GoPuff listings secured

- Target 50 independent health stores first 12 months

Priority 3 – Foodservice & Office

- Corporate wellness programs

- Gym chains (Equinox, Lifetime)

- University dining

#### Phase 6: Funding Requirements

- Seed/Pre-launch: $750K-$1.5M (R&D, IP, initial production)

- Series A (post $1-2M revenue): $5-10M (inventory + marketing war chest)

#### Phase 7: 12-Month Launch Timeline & KPIs

Month 1-3

- IP filed, co-packer contracted, DTC site build

Month 4-6

- First production run (10,000-25,000 units)

- Influencer seeding (500-1,000 micro/mid-tier health influencers)

- Waitlist campaign (target 25,000 emails)

Month 7 – Launch Day 1

- DTC live

- PR push (target TechCrunch, Well+Good, Food Navigator, Poosh)

- $200K-$400K first-month ad spend (Meta + TikTok)

Month 8-12 Goals

- $2.5M-$4M run-rate revenue by Month 12

- 35% repeat purchase rate

- 2-3 major retail chains PO’d for Q1 Year 2

#### Phase 8: Scaling Levers (Year 2+)

- International (Canada → UK/EU)

- Line extensions (new flavors, formats)

- Mass retail pitch (Target, Costco, Walmart) once velocity proven

Execute in this exact sequence to minimize cash burn and maximize probability of 8-figure exit within 4-5 years.